## Introduction
LIFE2 Case Study - British Library Newspapers
Burney Digital Newspapers - Lifecycle Processes and Costs
This spreadsheet contains the exact costings for the Burney Digital Collection that was used for the British Library Newspapers LIFE2 Case Study. There is a separate spreadsheet available for Legal Deposit Newspapers, as well as for the other case studies.
There are three sheets containing costs, available from the tabs below:
1. LIFEcycle Stages | This sheet gives all the costings on a stage, element, and sub-element level. It includes the way the costing was calculated, as well as a practical explanation of the process for each sub-element for this particular collection. For those people interested in detailed costs, this sheet will be of most use. For those more interested in the overall costs, the summary sheet will probably be of more use. By hovering the mouse over the LIFE terms, the full definition will appear in a pop-up box.
2. Cost calculations | Details some of the higher-level costs used in the calculations, for example the overall staff salary costs. These costs are then linked to the LIFE cost calculations. So, for example, you can edit the staff costs in this sheet, and the lifecycle costs on the other sheets will automatically update.
3. Summary | Gives an overall snapshot of the costs, as well as a summary graph of the lifecycle. It is also linked to the other sheets, so will automatically update if any changes are made to the calculations on other sheets.

## LIFEcycle stages
Burney Dígital Collection- Lifecycle Processes and Costs
v 2.0
Lifecycle Stages | Practical Explanation | Cost notes | % of Staff time | Year 1 (individual costs) | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | 5 year total | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | 10 year total
Creation or Purchase
Purchase |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Creation or Purchase | Cost to digitise the total archive plus create associated project information | creation of digital archive |  |  | 189710 | 129373 | 129373 | 0 | 0 | 0
Sub Total |  |  |  |  | 189710 | 129373 | 129373 | 0 | 0 | 448456 | 0 | 0 | 0 | 0 | 0 | 448456
Acquisition
Selection
Selection Policy (policy/procedure) |  | 10% Curatorial Grade B | 10% | 5556.32 | 5556.32 | 0 | 0 | 0 | 0 | 5556.32 | [5 empty] | 5556.32
Selection (action) | Sort Microfilm into correct order | 50% Curatorial Grade C, 6 months | 25% | 10713.15 | 10713.15 | 0 | 0 | 0 | 0 | 10713.15 | [5 empty] | 10713.15
Selection Metadata (metadata) | [9 empty] | 0 | [5 empty] | 0
Submission Agreement
Submission Agreement (policy/procedure) | Setting up of contract with third party | 10% project Grade A | 10% | 6647.62 | 6647.62 | 6647.62 | 6647.62 | 6647.62 | 0 | 26590.48 | [5 empty] | 26590.48
Negotiation of Submission (action) |  | 5% Legal support Grade A | 5% | 3323.81 | 3323.81 | 0 | 0 | 0 | 0 | 3323.81 | [5 empty] | 3323.81
Submission Metadata (documentation) | [9 empty] | 0 | [5 empty] | 0
IPR & Licensing
IPR & Licensing (policy/procedure) | Management of contract agreement with third party | 5% Product development Grade B | 5% | 2778.16 | 2778.16 | 0 | 0 | 0 | 0 | 2778.16 | [5 empty] | 2778.16
Negotiation of Rights (action) |  | 5% Product development Grade B | 5% | 2778.16 | 2778.16 | 0 | 0 | 0 | 0 | 2778.16 | [5 empty] | 2778.16
Negotiation of Licensing Agreement (action) | [9 empty] | 0 | [5 empty] | 0
Right Metadata (metadata) | [9 empty] | 0 | [5 empty] | 0
Ordering & Invoicing
Ordering & Re-ordering (action) | Compile list to order digital files | 10% project manager Grade A | 10% | 6647.62 | 6647.62 | 6647.62 | 6647.62 | 0 | 0 | 19942.86 | [5 empty] | 19942.86
Invoicing (action) |  | 25% project team (1) Grade C | 25% | 10713.15 | 10713.15 | 10713.15 | 10713.15 | 0 | 0 | 32139.45 | [5 empty] | 32139.45
Ordering Metadata (metadata) | [9 empty] | 0 | [5 empty] | 0
Obtaining
Obtaining (action) | Create work package and send order | 10% project manager Grade A | 10% | 6647.62 | 15218.14 | 15218.14 | 15218.14 | 15218.14 | 0 | 60872.56 | [5 empty] | 60872.56
|  | 20% project team (1) Grade C | 20% | 8570.52
Obtaining Metadata (metadata) | [9 empty] | 0 | [5 empty] | 0
Check in
Content Check (action) | Receive work package and quick check | 10% project manager Grade A | 10% | 6647.62 | 6647.62 | 6647.62 | 6647.62 | 6647.62 | 0 | 26590.48 | [5 empty] | 26590.48
Fixity Check (action) |  | 25% project team (2) Grade C, 12.5% for Year 4. | 25% | 10713.15 | 10713.15 | 10713.15 | 10713.15 | 5356.575 | 0 | 37496.025 | [5 empty] | 37496.025
Check-in Metadata (metadata) | [9 empty] | 0 | [5 empty] | 0
Sub Total |  |  |  |  | 81736.9 | 56587.3 | 56587.3 | 33869.955 | 0 | 228781.455 | 0 | 0 | 0 | 0 | 0 | 228781.455
Ingest
Quality Assurance
QA Policy (policy/procedure) | [9 empty] | 0 | [5 empty] | 0
QA Characterisation (action) | [9 empty] | 0 | [5 empty] | 0
Content Examination (action) | Detailed check of work package fixity values and virus checking | 25% project team (2) Grade C, 12.5% in Year 4. | 25% | 10713.15 | 17360.77 | 17360.77 | 17360.77 | 8680.385 | 0 | 60762.695 | [5 empty] | 60762.695
| Manager’s time checking Burney server to confirm all expected content is present. | 10% Project Manager Grade A, 5% in Year 4 | 10% | 6647.62 |  |  |  |  | 0
Mitigation (action) |  | 25% project team (2) Grade C, 12.5% in Year 4. | 25% | 10713.15 | 10713.15 | 10713.15 | 10713.15 | 5356.575 | 0 | 37496.025 | [5 empty] | 37496.025
QA Metadata (metadata) | [9 empty] | 0 | [5 empty] | 0
Deposit
Deposit (action) | Move from tapes to server | 25% project team (2) Grade C, | 25% | 10713.15 | 12855.78 | 12855.78 | 12855.78 | 0 | 0 | 38567.34 | [5 empty] | 38567.34
|  | 5% project team (1) Grade C | 5% | 2142.63
Deposit Metadata (action) | [9 empty] | 0 | [5 empty] | 0
Holdings Update
Holdings Update (action) | Update server database | 20% project team (1) Grade C, 10% in Year 4. | 20% | 8570.52 | 8570.52 | 8570.52 | 8570.52 | 4285.26 | 0 | 29996.82 | [5 empty] | 29996.82
Holdings Update Metadata (metadata) |  | 20% project team (1) Grade C, 10% in Year 4. | 20% | 8570.52 | 8570.52 | 8570.52 | 8570.52 | 4285.26 | 0 | 29996.82 | [5 empty] | 29996.82
Reference Linking
Create Search Indices (action) | [9 empty] | 0 | [5 empty] | 0
Reference Linking (action) | [9 empty] | 0 | [5 empty] | 0
Reference Linking Metadata (metadata) | [9 empty] | 0 | [5 empty] | 0
Sub Total |  |  |  |  | 58070.74 | 58070.74 | 58070.74 | 22607.48 | 0 | 196819.7 | 0 | 0 | 0 | 0 | 0 | 196819.7
Metadata Creation
Re-use Existing Metadata | Export information to Aleph | 10% project team (1) Grade C | 10% | 4285.26 | 4285.26 | 0 | 0 | 0 | 0 | 4285.26 | [5 empty] | 4285.26
Metadata Creation | Additional information added to BL records. Arrival date, QA signoff | 20% project manager Grade A | 20% | 13295.24 | 13295.24 | 13295.24 | 13295.24 | 0 | 0 | 39885.72 | [5 empty] | 39885.72
Metadata Extraction | Extraction of OCR for resource discovery | Part of total creation cost to OCR clean and segment files | [7 empty] | 0 | [5 empty] | 0
Sub Total |  |  |  |  | 17580.5 | 13295.24 | 13295.24 | 0 | 0 | 44170.98 | 0 | 0 | 0 | 0 | 0 | 44170.98
Bit-stream Preservation
Repository Administration
System Technology Watch (action) | [9 empty] | 0 | [5 empty] | 0
System Security (action) | Time taken to manage the server | 3.3% Project Manager Grade A, 1.65% in Year 4 | 3.333% | 2215.8731 | 2215.8731 | 2215.8731 | 2215.8731 | 1107.9366 | 0 | 7755.5559 | [5 empty] | 7755.5559
Statistics and Reporting (action) | [9 empty] | 0 | [5 empty] | 0
Disaster Recovery Planning (action) | [9 empty] | 0 | [5 empty] | 0
Manage Duplicate Storage (action) | [9 empty] | 0 | [5 empty] | 0
Storage Procurement (action) | [9 empty] | 0 | [5 empty] | 0
Storage Provision
Storage hardware (technology) | Burney project hard drive costs | Server cost |  | 4899 | 4899 | 0 | 0 | 0 | 0 | 4899 | [5 empty] | 4899
Storage Maintenance and Support (action) | Time taken to add new hardware | 3.3% Project Manager Grade A, 1.65% in Year 4 | 3.333% | 2215.8731 | 2215.8731 | 2215.8731 | 2215.8731 | 1107.9366 | 0 | 7755.5559 | [5 empty] | 7755.5559
Refreshment
Refreshment (action) | Time taken to move the data from tape to server | 3.3% Project Manager Grade A, 1.65% in Year 4 | 3.333% | 2215.8731 | 2215.8731 | 2215.8731 | 2215.8731 | 1107.9366 | 0 | 7755.5559 | [5 empty] | 7755.5559
Backup
Backup Procedure (policy/procedure) | Cost of creating LTO3 tapes for the project | IT Function cost calculated is estimated from similar areas | [7 empty] | 0 | [5 empty] | 0
Backup (action) | [9 empty] | 0 | [5 empty] | 0
Recovery (action) | [9 empty] | 0 | [5 empty] | 0
Inspection
Fixity Audit (action) | [9 empty] | 0 | [5 empty] | 0
Manual Inspection (action) | Visual inspection of bit stream to ensure that it can be viewed. | 10% Project Manager Grade A | 10% | 6647.62 | 6647.62 | 0 | 0 | 0 | 0 | 6647.62 | [5 empty] | 6647.62
Inspection Metadata (metadata) | [9 empty] | 0 | [5 empty] | 0
Sub Total |  |  |  |  | 18194.2393 | 6647.6193 | 6647.6193 | 3323.8097 | 0 | 34813.2877 | 0 | 0 | 0 | 0 | 0 | 34813.2877
Content Preservation
Preservation Watch
Technology Watch (action) | Time allocated to preservation watch activity for Burney by The British Library’s Digital Preservation team | 2% Digital Preservation Team Grade A | 2% | 0 | 0 | 0 | 0 | 1329.524 | 1329.524 | 2659.048 | [5 empty] | 2659.048
Monitor Institution (action) | [9 empty] | 0 | [5 empty] | 0
Monitor User Community (action) |  | 2% Digital Preservation Team Grade A | 2% | 0 | 0 | 0 | 0 | 1329.524 | 1329.524 | 2659.048 | [5 empty] | 2659.048
Monitor Producer (action) | [9 empty] | 0 | [5 empty] | 0
Record Planning Requirements (metadata) | [9 empty] | 0 | [5 empty] | 0
Preservation Planning
Preservation Planning (action) | Time taken to create preservation plan for Burney based upon preservation watch | Cost of writing a preservation plan |  | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | [5 empty] | 5000
Record/Update Preservation Metadata (metadata) | [9 empty] | 0 | [5 empty] | 0
Preservation Action
Integrate new preservation solution (action) | [9 empty] | 0 | [5 empty] | 0
Perform Preservation Action (action) | Time taken by Digital preservation team to secure the archive. | 5% Digital Preservation Team Grade A | 5% | 0 | 0 | 0 | 0 | 3323.81 | 3323.81 | 6647.62 | [5 empty] | 6647.62
QA Preservation Action (action) | [9 empty] | 0 | [5 empty] | 0
Record Preservation Action Metadata (metadata) |  | 2% Digital Preservation Team Grade A | 2% | 0 | 0 | 0 | 0 | 1329.524 | 1329.524 | 2659.048 | [5 empty] | 2659.048
Re-ingest
Obtaining | Gather new files from preservation action and re-ingest into project server | [8 empty] | 0 | [5 empty] | 0
Check-in | [9 empty] | 0 | [5 empty] | 0
Quality Assurance | [9 empty] | 0 | [5 empty] | 0
Characterisation and Metadata Extraction | [9 empty] | 0 | [5 empty] | 0
Deposit | [9 empty] | 0 | [5 empty] | 0
Holdings Update | [9 empty] | 0 | [5 empty] | 0
Sub Total |  |  |  |  | 0 | 0 | 0 | 12312.382 | 7312.382 | 19624.764 | 0 | 0 | 0 | 0 | 0 | 19624.764
Access
Access Provision
Access Provision (action) | The cost of setting up the web application to view the files | 10% Project Manager Grade A | 10% | 6647.62 | 32847.62 | 30647.62 | 6647.62 | 0 | 0 | 70142.86 | [5 empty] | 70142.86
|  | setup costs | Year 1 = 26,200, Year 2 = 24,000 | 26200
Rendering and representation (action) | [9 empty] | 0 | [5 empty] | 0
Record Access metadata (metadata) | [9 empty] | 0 | [5 empty] | 0
Access Control
Access Control (action) | The cost to manage the projects digital rights management based upon the licensing agreements | 5% Product development Grade B | 5% | 2778.16 | 2778.16 | 0 | 0 | 0 | 0 | 2778.16 | [5 empty] | 2778.16
Technical Protection Measures (action) | [9 empty] | 0 | [5 empty] | 0
Record Access metadata (metadata) | [9 empty] | 0 | [5 empty] | 0
User Support
User Support (action) | The cost to support users who access the digital objects. | [8 empty] | 0 | [5 empty] | 0
Sub Total |  |  |  |  | 35625.78 | 30647.62 | 6647.62 | 0 | 0 | 72921.02 | 0 | 0 | 0 | 0 | 0 | 72921.02
TOTAL |  |  |  |  | 400918.1593 | 294621.5193 | 270621.5193 | 72113.6267 | 7312.382 | 1045587.2067 | 0 | 0 | 0 | 0 | 0 | 1045587.2067
Note on A15: Development of Selection Policy for the collection.
Note on A16: The application of the selection process, guided by the Selection Policy.
Note on A17: Recording of metadata describing the scope, results and justification for the selection decisions.
Note on A19: Specification of submission requirements for producers/depositors.
Note on A20: Communication and negotiation with producers/depositors.
Note on A21: Recording of metadata relating to submission requirements.
Note on A23: This might include investigating the current IPR situation and who the relevant IPR holders are.
Note on A24: Negotiation of rights to preserve and provide access with producers/depositors.
Note on A25: Negotiation of rights to provide access with producers/depositors.
Note on A26: Recording of right metadata.
Note on A28: Ordering and re-ordering of the object, where it has been found to be of an insufficient level of quality during the Check-in or Quality Assurance processes.
Note on A29: invoicing and administration for payments made.
Note on A30: Record ordering and invoicing metadata.
Note on A32: Transport of the object to the preserving organisation.
Note on A34: Record obtaining metadata.
Note on A36: Verify titles, issues, filenames.
Note on A37: Verify checksums.
Note on A38: Record check-in metadata.
Note on A43: Description of quality requirements and required mitigation actions should quality requirements not be met. Policy for sampling of objects for QA (if applicable).
Note on A44: Characterisation of the digital objects. Identification of file format, and assessment of whether the object is valid, well formed, and/or renders correctly with current access software.
Note on A45: Assessment of whether the content of the digital object is of an expected, agreed or sufficient level of quality. Typically, a manual process on a sample of the ingested objects.
Note on A47: Action to mitigate quality issues (might include virus cleaning or re-ordering or obtaining the digital object).
Note on A48: Record QA metadata.
Note on A50: Commit the digital object to the repository.
Note on A52: Record Deposit metadata.
Note on A54: Update holdings records.
Note on A55: Record Holdings Update metadata.
Note on A57: Creation of indices for use within search engines.
Note on A58: Linking the object to entries in relevant finding aids.
Note on A59: Record Reference Linking metadata.
Note on A63: where metadata accompanying the ingested digital object is stored, converted or reuses.
Note on A64: where new metadata is created, typically as part of a manual cataloguing process
Note on A65: where metadata is extracted from the digital object, typically as part of an automated characterisation or metadata extraction process.
Note on A70: Monitoring for the need to upgrade or update systems or hardware due to technology obsolescence.
Note on A71: Maintenance and auditing of repository system security.
Note on A72: Recording and reporting of statistics.
Note on A73: Planning for recovery and re-establishment of the repository in the event of disaster.
Note on A74: Management processes associated with effective maintenance and synchronisation of multiple node storage.
Note on A75: Procurement of storage hardware.
Note on A77: Costs associated with hardware purchases.
Note on A78: Maintenance and support necessary to keep the storage fully functional over time.
Note on A80: Moving digital objects to new hardware.
Note on A82: Development of backup policy and procedure.
Note on A83: Planned backup activity.
Note on A84: Irregular (and hopefully infrequent) recovery of data from backups.
Note on A86: Automated auditing of stored objects ensuring matching re-generated checksums with previously sorted checksums to identify changes or loss of content.
Note on A87: Manually inspection of a sample of digital objects to ensure they can be retrieved and rendered as expected.
Note on A88: Record Inspection metadata.
Note on A93: Focusing on technology changes in areas such as file formats, rendering tools, environments.
Note on A94: Capturing preservation planning requirements from the preserving organisations preservation policy and broader organisational strategy.
Note on A95: Gathering requirements influenced by the end users of the objects.
Note on A96: Monitoring of the producer of the digital objects (if applicable).
Note on A97: Recording of requirements for preservation planning based on information gathered by preservation watch activities.
Note on A99: Assessment of planning requirements and preservation solutions, and development of preservation plans.
Note on A100: Updating preservation metadata, such as Representation solutions, and development of preservation plans.
Note on A102: Obtain/integrate new preservation action tool.
Note on A103: Updating preservation metadata, such as Representation Information, based on preservation planning conclusions.
Note on A104: Perform an evaluation and quality assurance.
Note on A105: Record Preservation Action metadata.
Note on A117: Retrieval of digital objects and Provision of access to users.
Note on A119: Provision of software and/or information to facilitate rendering of the digital objects by the user.
Note on A120: Record usage metadata.
Note on A122: Restriction of access to those users allowed to use the digital objects.
Note on A123: Restriction of uses of the digital objects.
Note on A124: Record usage metadata.
Note on C77: See details in Cost Calculation --> Burney Project Capital Cost
Note on C118: See details in Cost Calculation --> Burney Project Capital Cost

## Cost calculations
Costs used for LIFE Model (Burney Digital Newspapers)
Staff Cost (£) - 2007
Grade | Average Annual Staff Cost | 40% Overhead | Cost Including Overhead
SB3 | 84612 | 33844.8 | 118456.8
SB4 | 63171 | 25268.4 | 88439.4
A | 47483 | 18993.2 | 66476.2
B | 39688 | 15875.2 | 55563.2
C | 30609 | 12243.6 | 42852.6
D | 25589 | 10235.6 | 35824.6
E | 24554 | 9821.6 | 34375.6
There are 1100 volumes of burney newspapers
There are 1,000,000 pages of these volumes
There are 916,652 digital objects (TIFF plus XML= 1 object)
Burney Project Capital Cost (£)
Type | 2005 | 2006 | 2007
Setup Cost | 26200 | 24000 | 0
Hard drive (server) cost | 4899 | 0 | 0
Lifecycle cost over 5 years - Burney
Number of digital objects | 190256
Number of digital items | 916652
Total cost over 5 years (£) | 1045587.2067
Cost per digital item (£) | 1.1407
Cost per digital object (£) | 5.4957

## Summary
Summary of LIFE Costs for Burney Digital Newspapers
Burney Digital Collection -- Lifecycle Cost in 5 years
Stages | C | Aq | I | M | BP | CP | Ac | Total
Cost | 448456 | 228781.455 | 196819.7 | 44170.98 | 34813.2877 | 19624.764 | 72921.02 | 1045587.2067
Burney Digital Collection -- Per entity cost in 5 years
Stages | C | Aq | I | M | BP | CP | Ac | Total
Cost | 2.3571 | 1.2025 | 1.0345 | 0.23217 | 0.18298 | 0.10315 | 0.38328 | 5.4957